## Cover
NUOVE — PRODUCT REQUIREMENTS DOCUMENT
Version 1.0 ¦ App Store & Play Store Launch ¦ Prepared by: Product Owner
APP OVERVIEW
App Name |  |  | Nuove
Domain |  |  | nuove.in
Platform |  |  | iOS App Store + Google Play Store + Web (nuove.in)
Frontend |  |  | React + Vite → Vercel ¦ Capacitor wrapper for native apps
Backend |  |  | Node.js + Express → Railway
Database |  |  | PostgreSQL (to be provisioned)
Payments |  |  | Razorpay (India)
Target Users |  |  | Indian short-form video creators (Instagram Reels, YouTube Shorts)
Target Launch |  |  | TBD — all P1 items must be complete before submission
PRIORITY GUIDE
P1 – Must Have |  |  | Blocker — app CANNOT launch without this. Do first.
P2 – Should Have |  |  | Important — do within Week 1 of development sprint.
P3 – Nice to Have |  |  | Good UX improvement — do within Month 1.
P4 – Future |  |  | Post-launch backlog. Schedule after first 500 users.
MODULE SUMMARY
Code | Module | Stories | P1 | P2 | P3 | P4 | Est. Hrs
AUTH | Authentication & Onboarding | 11 | 7 | 3 | 1 | 0 | 42
DASH | Dashboard | 5 | 2 | 3 | 0 | 0 | 18
GEN | Script Generator | 8 | 4 | 3 | 1 | 0 | 32
REC | Teleprompter & Recorder | 9 | 5 | 3 | 1 | 0 | 35
HIST | Script History | 5 | 2 | 1 | 2 | 0 | 16
CROSS | Crosspost | 5 | 3 | 1 | 1 | 0 | 16
PROF | Profile & Settings | 7 | 2 | 4 | 1 | 0 | 22
PAY | Payments & Subscriptions | 11 | 6 | 3 | 2 | 0 | 44
NOTIF | Notifications & Email | 6 | 2 | 1 | 2 | 1 | 18
MOB | Mobile App – iOS & Android | 12 | 7 | 3 | 1 | 1 | 52
INFRA | Backend & Infrastructure | 9 | 5 | 3 | 1 | 0 | 30
TEST | Testing & QA | 8 | 4 | 3 | 1 | 0 | 32
SEC | Security | 7 | 6 | 1 | 0 | 0 | 24
LEGAL | Legal & Compliance | 6 | 4 | 2 | 0 | 0 | 16
PERF | Performance & Analytics | 7 | 3 | 3 | 1 | 0 | 22
| TOTAL | 116 |  |  |  |  | 2

## User Stories
NUOVE — User Stories & Acceptance Criteria
ID | Module | User Story | Acceptance Criteria | Priority | Platform | Est. Hrs | Status | Assigned To | Notes
▸ AUTH & ONBOARDING
AUTH-01 | Auth & Onboarding | As a new user, I want to sign up with my email and password so I can create an account. | • Sign up form has: Name, Email, Password, Confirm Password fields • Password min 8 chars, must include 1 number • Shows inline error if email already registered • Shows inline error if passwords don't match • On success → redirect to onboarding step 1 • Sends welcome email on signup • Password stored as bcrypt hash (never plain text) | P1 – Must Have | All | 4 | Not Started | Intern
AUTH-02 | Auth & Onboarding | As a user, I want to sign in with Google so I don't have to remember a password. | • 'Continue with Google' button on login and signup screen • Clicking opens Google OAuth popup • On success → new users go to onboarding, existing users go to Dashboard • Profile photo from Google is stored as avatar • If Google email matches existing account → merged automatically | P1 – Must Have | All | 5 | Not Started | Intern
AUTH-03 | Auth & Onboarding | As an iOS user, I want to sign in with Apple ID so I can use the app per App Store requirements. | • 'Sign in with Apple' button visible on iOS only • Apple Sign In is MANDATORY for App Store (Apple rule) • Returns name + email (or private relay email) • New Apple users go to onboarding • Handles 'hide my email' relay correctly | P1 – Must Have | iOS | 6 | Not Started | Intern
AUTH-04 | Auth & Onboarding | As a returning user, I want to log in and stay logged in so I don't log in every time. | • JWT access token (15 min expiry) + refresh token (30 day expiry) • Refresh token stored in httpOnly cookie • App auto-refreshes token silently in background • User stays logged in for 30 days without re-entering password • 'Remember me' checkbox on login screen | P1 – Must Have | All | 4 | Not Started | Intern
AUTH-05 | Auth & Onboarding | As a user who forgot my password, I want to reset it via email. | • 'Forgot password?' link on login screen • Enter email → receive reset link within 60 seconds • Reset link expires after 1 hour • New password form: min 8 chars, confirm field • On success → auto login → redirect to Dashboard • Old sessions invalidated after reset | P1 – Must Have | All | 3 | Not Started | Intern
AUTH-06 | Auth & Onboarding | As a new user, I want an onboarding flow so I can set up my profile before using the app. | • Step 1: Choose your niche (select 1–3 from: Fitness, Food, Fashion, Finance, Tech, Travel, Comedy, Education, Other) • Step 2: Choose primary platform (Instagram Reels / YouTube Shorts / Both) • Step 3: Choose language (English, Hindi, Hinglish, Tamil, Telugu, Other) • Step 4: 'Generate your first script' CTA • Progress bar showing step X of 4 • Can skip onboarding (goes to Dashboard) • Selections saved to user profile in DB | P1 – Must Have | All | 5 | Not Started | Intern
AUTH-07 | Auth & Onboarding | As a user, I want to see a splash screen when the app opens so it feels like a real native app. | • App icon + 'Nuove' wordmark centred on brand gradient background • Visible for 1.5 seconds max • Does not show on subsequent app opens if already logged in (goes straight to Dashboard) • Required for App Store / Play Store | P1 – Must Have | iOS, Android | 2 | Not Started | Intern
AUTH-08 | Auth & Onboarding | As a user, I want to log out securely from any device. | • Logout button in Profile / Settings • Clears JWT tokens from storage • Invalidates refresh token on server • Redirects to login screen • 'Log out of all devices' option in settings | P1 – Must Have | All | 2 | Not Started | Intern
AUTH-09 | Auth & Onboarding | As a user, I want to delete my account and all my data. | • 'Delete Account' option in Settings → Account • Confirmation modal: type 'DELETE' to confirm • Deletes: user record, all scripts, recordings metadata, payment history • Cancels active subscription via Razorpay • Sends confirmation email • Required by DPDP Act 2023 (India) | P2 – Should Have | All | 4 | Not Started | Intern
AUTH-10 | Auth & Onboarding | As a user on the app for the first time, I want a short product tour so I understand the features. | • 3-slide carousel after onboarding (skippable) • Slide 1: Generate Scripts • Slide 2: Teleprompter & Recorder • Slide 3: Crosspost everywhere • 'Get Started' button on last slide → Dashboard • Never shown again after first view | P2 – Should Have | All | 3 | Not Started | Intern
AUTH-11 | Auth & Onboarding | As a user, I want to see a proper loading/error state if login fails. | • Button shows spinner while API call in progress • Button is disabled while loading (prevents double submit) • Wrong password → 'Incorrect email or password' • Account locked → 'Too many attempts. Try in 15 minutes.' • Network error → 'No internet connection. Please try again.' • No white screen of death under any circumstance | P1 – Must Have | All | 2 | Not Started | Intern
▸ DASHBOARD
DASH-01 | Dashboard | As a user, I want to see a personalised greeting on my Dashboard so the app feels mine. | • Shows 'Good morning/afternoon/evening, [First Name]' • Greeting uses current device time • Gradient text using brand colours • Sub-line shows today's date and a motivational tip (rotates daily) | P2 – Should Have | All | 2 | Not Started | Intern
DASH-02 | Dashboard | As a user, I want to see my weekly stats on the Dashboard so I can track my progress. | • Shows: Scripts Generated (this week), Recordings Made (this week), Current Streak (days) • Streak = consecutive days where user generated at least 1 script • Numbers animate on load (count up) • Empty state: '0 scripts this week — let's fix that!' | P2 – Should Have | All | 4 | Not Started | Intern
DASH-03 | Dashboard | As a user, I want quick-access shortcuts on the Dashboard to my most-used features. | • 4 shortcut cards: Generate Script, Record, Crosspost, Trending • Tapping any card navigates to that feature • Cards show icon + label • Visually matches brand design | P2 – Should Have | All | 3 | Not Started | Intern
DASH-04 | Dashboard | As a user, I want to see my last 3 saved scripts on the Dashboard. | • Shows 3 most recent scripts (truncated to 2 lines) • 'View All' link → Script History page • Empty state: 'No scripts yet. Generate your first one!' • Tapping a script → opens it in Script History | P3 – Nice to Have | All | 3 | Not Started | Intern
DASH-05 | Dashboard | As a user, I want a 'content tip of the day' card on the Dashboard. | • Single tip card (e.g. 'Hooks under 3 seconds get 2x more saves') • Rotates daily from a pool of 30 tips • Tip is relevant to the user's chosen niche • Tap to dismiss | P3 – Nice to Have | All | 3 | Not Started | Intern
▸ SCRIPT GENERATOR
GEN-01 | Script Generator | As a creator, I want to generate a full video script by describing my topic. | • Input field: 'What's your video about?' (max 200 chars) • Auto-detect niche from onboarding (shown as tag, can change) • Auto-detect language (can change via dropdown) • Platform selector: Reels / Shorts / Both • Tone selector: Funny, Educational, Motivational, Controversial, Storytelling • 'Generate Script' button • Shows loading spinner during generation • Streams response (text appears word by word) | P1 – Must Have | All | 6 | Not Started | Intern
GEN-02 | Script Generator | As a creator, I want the generated script to be structured with a Hook, Body and CTA. | • Script output has 3 clearly labelled sections: – Hook (first 3 seconds — attention grabber) – Body (main content, 30–45 seconds) – CTA (call to action, last 5 seconds) • Each section has a copy button • Character count per section • Total estimated video duration shown | P1 – Must Have | All | 4 | Not Started | Intern
GEN-03 | Script Generator | As a creator, I want to save a generated script so I can use it later. | • 'Save Script' button below generated output • Saves to DB linked to user account (not just localStorage) • Shows toast: 'Script saved!' • Saved scripts appear in Script History • User can name the script (optional, defaults to topic) | P1 – Must Have | All | 4 | Not Started | Intern
GEN-04 | Script Generator | As a creator, I want to regenerate a script if I don't like the first result. | • 'Regenerate' button next to Save • Generates a new version with same inputs • Previous version is NOT lost (shown as 'Version 1' vs 'Version 2') • Max 3 free regenerations per script (then prompts upgrade) | P2 – Should Have | All | 3 | Not Started | Intern
GEN-05 | Script Generator | As a creator, I want to copy the full script to clipboard with one tap. | • 'Copy All' button copies entire script (Hook + Body + CTA) • Toast confirmation: 'Copied to clipboard' • Works on mobile browsers (uses navigator.clipboard API with fallback) | P1 – Must Have | All | 1 | Not Started | Intern
GEN-06 | Script Generator | As a creator, I want to go directly to the Teleprompter with my saved script. | • 'Record This' button on generated script • Tapping saves script to sessionStorage and navigates to /record • Teleprompter loads with the script pre-filled • No need to copy-paste manually | P1 – Must Have | All | 2 | Not Started | Intern
GEN-07 | Script Generator | As a free-tier user, I want to know how many script generations I have left. | • Free plan: 5 generations per month • Counter shown: 'X of 5 generations used this month' • On hitting limit: modal appears with upgrade prompt • Counter resets on 1st of each month • Pro plan: unlimited generations | P2 – Should Have | All | 4 | Not Started | Intern
GEN-08 | Script Generator | As a creator, I want to generate scripts in multiple Indian languages. | • Language options: English, Hindi, Hinglish, Tamil, Telugu, Kannada, Bengali • Language selector visible in generate form • Script generated in selected language • Language saved to user preference automatically | P2 – Should Have | All | 3 | Not Started | Intern
▸ TELEPROMPTER & RECORDER
REC-01 | Teleprompter & Recorder | As a creator, I want to see my script scroll automatically while recording so I don't need a second device. | • Script text displayed large, centred on screen • Auto-scroll starts when recording begins • Auto-scroll pauses when recording is paused • Speed control: 7 levels (Very Slow to Fast) • Font size control: Small / Medium / Large • Text is white on dark background for readability | P1 – Must Have | All | 5 | Not Started | Intern
REC-02 | Teleprompter & Recorder | As a creator, I want to record video using my front camera while reading the teleprompter. | • Requests camera + microphone permission on first use • Front camera selected by default • Camera feed visible behind the script text • Permission denied → shows 'Please allow camera access in Settings' • Works on iOS Safari, Android Chrome, and web | P1 – Must Have | All | 6 | Not Started | Intern
REC-03 | Teleprompter & Recorder | As a creator, I want a countdown before recording starts so I can get ready. | • 3-2-1 countdown displayed large before recording starts • Countdown sound (optional, can mute) • Recording indicator (red dot + 'REC' label) visible during recording | P1 – Must Have | All | 2 | Not Started | Intern
REC-04 | Teleprompter & Recorder | As a creator, I want to pause and resume recording. | • Pause button visible during recording • Pausing freezes teleprompter scroll • Resuming continues from same position • Recording timer pauses when paused • Final video is continuous (no gap at pause point) | P2 – Should Have | All | 4 | Not Started | Intern
REC-05 | Teleprompter & Recorder | As a creator, I want to preview and download my recording when done. | • After stopping, show video playback • 'Download' button saves video to device • Download filename: nuove-recording.mp4 • iOS: shows share sheet (save to Files / Photos) • Android: saves to Downloads folder | P1 – Must Have | All | 4 | Not Started | Intern
REC-06 | Teleprompter & Recorder | As a creator, I want to manually type or paste a script into the teleprompter. | • Text area to enter script manually • Pre-filled if arriving from Generate page • Can edit text directly in the teleprompter setup screen • 'Clear' button to remove all text | P1 – Must Have | All | 2 | Not Started | Intern
REC-07 | Teleprompter & Recorder | As a creator on iOS, I want my recording to work in the correct format. | • iOS Safari does not support webm — use video/mp4 or video/quicktime • Detect browser/OS and select correct codec automatically • Test on: iPhone 12, 13, 14 (iOS 15, 16, 17) • File plays correctly in iPhone Camera Roll | P1 – Must Have | iOS | 5 | Not Started | Intern
REC-08 | Teleprompter & Recorder | As a creator, I want the recorder to work in fullscreen on mobile. | • Entering record mode requests fullscreen on Android (Fullscreen API) • On iOS: full viewport height (no browser chrome) • Teleprompter text fills screen • Back button / swipe exits recording safely (with confirmation if recording active) | P2 – Should Have | iOS, Android | 3 | Not Started | Intern
REC-09 | Teleprompter & Recorder | As a creator, I want to switch between front and back camera. | • Camera switch button (flip icon) visible on recorder • Switches camera without stopping recording session • Camera restarts with new facing mode | P3 – Nice to Have | iOS, Android | 3 | Not Started | Intern
▸ SCRIPT HISTORY
HIST-01 | Script History | As a creator, I want to see all my saved scripts in one place. | • List of all saved scripts, newest first • Each item shows: Title, Date saved, First 2 lines of script • 'Load More' / pagination for >20 scripts • Empty state: 'No scripts yet. Generate your first one!' + CTA button | P1 – Must Have | All | 3 | Not Started | Intern
HIST-02 | Script History | As a creator, I want to open and read a saved script in full. | • Tap script → opens full view (modal or new screen) • Full Hook / Body / CTA sections visible • Copy button per section and 'Copy All' • 'Record This' button → opens Teleprompter with script | P1 – Must Have | All | 3 | Not Started | Intern
HIST-03 | Script History | As a creator, I want to delete scripts I no longer need. | • Delete button (trash icon) on each script • Confirmation: 'Delete this script? This cannot be undone.' • On confirm → removed from list with animation • Synced to DB (deletion is permanent) | P2 – Should Have | All | 2 | Not Started | Intern
HIST-04 | Script History | As a creator, I want to search my saved scripts. | • Search bar at top of Scripts page • Filters list in real time by script title or content • No results state: 'No scripts match your search' | P3 – Nice to Have | All | 3 | Not Started | Intern
HIST-05 | Script History | As a creator, I want to share a script with someone via a link. | • 'Share' button on each script • Generates a public read-only URL: nuove.in/s/[unique-id] • Anyone with link can view (no login required) • Shared view is read-only — no edit/delete • 'Copy Link' copies URL to clipboard | P3 – Nice to Have | All | 5 | Not Started | Intern
▸ CROSSPOST
CROSS-01 | Crosspost | As a creator, I want to write a caption once and format it for all platforms. | • Input: paste your script or video topic • Select platforms: Instagram, YouTube, TikTok, LinkedIn, Twitter/X • AI generates platform-optimised captions for each selected platform • Each caption follows platform best practices (length, hashtag count, tone) | P1 – Must Have | All | 5 | Not Started | Intern
CROSS-02 | Crosspost | As a creator, I want the captions to include relevant hashtags. | • Each caption includes 5–15 relevant hashtags • Hashtags are researched per platform norms • Instagram: 10–15 hashtags • YouTube: 3–5 hashtags in description • TikTok: 5–8 hashtags • Hashtags can be edited by user | P1 – Must Have | All | 3 | Not Started | Intern
CROSS-03 | Crosspost | As a creator, I want to copy any platform caption with one tap. | • 'Copy' button per platform caption • Toast: 'Copied!' • Works on mobile (navigator.clipboard with textarea fallback) • Entire caption + hashtags copied together | P1 – Must Have | All | 1 | Not Started | Intern
CROSS-04 | Crosspost | As a creator, I want to generate captions in different languages. | • Language selector in Crosspost page • Options: English, Hindi, Hinglish, Tamil, Telugu, Kannada • All platform captions generated in selected language • Language preference remembered from last use | P2 – Should Have | All | 3 | Not Started | Intern
CROSS-05 | Crosspost | As a creator, I want to regenerate a specific platform's caption if I don't like it. | • 'Regenerate' icon button on each platform's caption card • Only regenerates that platform's caption (others unchanged) • Shows spinner on that card only • Previous version replaced on success | P3 – Nice to Have | All | 3 | Not Started | Intern
▸ PROFILE & SETTINGS
PROF-01 | Profile & Settings | As a user, I want to view and edit my profile information. | • Shows: Name, Email, Profile Photo, Niche, Platform preference, Language • Edit Name: inline text field • Edit profile photo: tap photo → image picker • Email change requires current password confirmation • Save button → updates DB → shows success toast | P1 – Must Have | All | 4 | Not Started | Intern
PROF-02 | Profile & Settings | As a user, I want to change my password from within the app. | • Settings → Security → Change Password • Fields: Current Password, New Password, Confirm New Password • Validates current password before allowing change • All existing sessions logged out after change • Success toast + email notification sent | P2 – Should Have | All | 3 | Not Started | Intern
PROF-03 | Profile & Settings | As a user, I want to see my subscription plan and usage in Profile. | • Shows current plan: Free / Pro / Creator • Shows usage: X of 5 script generations used • 'Upgrade' button → Pricing page • 'Manage Subscription' → Billing page (for paid users) | P1 – Must Have | All | 3 | Not Started | Intern
PROF-04 | Profile & Settings | As a user, I want to control notification preferences. | • Toggle: Email notifications (weekly tips, feature updates) • Toggle: Push notifications (if PWA/native app) • Toggle: Marketing emails • Saved to user preferences in DB | P3 – Nice to Have | All | 3 | Not Started | Intern
PROF-05 | Profile & Settings | As a user, I want to toggle between dark and light mode. | • Toggle in Settings or Profile page • Defaults to system preference (prefers-color-scheme) • Preference saved to localStorage • All pages must look correct in both modes | P2 – Should Have | All | 3 | Not Started | Intern
PROF-06 | Profile & Settings | As a user, I want to see the app version, Terms, Privacy Policy and support links. | • Settings → About section • App version number • Links: Terms & Conditions, Privacy Policy, Contact Support • Links open in in-app browser (not external browser) • 'Rate this App' link (iOS: App Store, Android: Play Store) | P2 – Should Have | All | 2 | Not Started | Intern
PROF-07 | Profile & Settings | As a user, I want to change my content niche and language preference. | • Settings → Preferences • Niche multi-select (same options as onboarding) • Language dropdown • Platform preference: Reels / Shorts / Both • Changes apply to all future script generations | P2 – Should Have | All | 2 | Not Started | Intern
▸ PAYMENTS & SUBSCRIPTIONS
PAY-01 | Payments & Subscriptions | As a user, I want to see a pricing page with clear plan comparison. | • 3 tiers: Free, Pro, Creator • Feature comparison table (what's included in each) • Monthly / Annual toggle (Annual = 2 months free) • 'Most Popular' badge on Pro plan • CTA: 'Start Free', 'Go Pro', 'Go Creator' • INR pricing shown (₹) | P1 – Must Have | All | 5 | Not Started | Intern
PAY-02 | Payments & Subscriptions | As a user, I want to subscribe using Razorpay with my UPI, card or net banking. | • 'Subscribe' button opens Razorpay checkout • Razorpay checkout handles: UPI, Cards, Net Banking, Wallets • Live Razorpay keys configured (not test keys) • On payment success → plan activated immediately • On payment failure → friendly error message, not a white screen | P1 – Must Have | All | 5 | Not Started | Intern
PAY-03 | Payments & Subscriptions | As a subscribed user, my features unlock immediately after payment. | • Razorpay webhook: payment.captured → update user plan in DB • Frontend polls or receives socket event to update plan • Feature gates re-check user plan in real time • No manual refresh needed to see unlocked features | P1 – Must Have | All | 5 | Not Started | Intern
PAY-04 | Payments & Subscriptions | As a subscribed user, I want to see my billing history and invoices. | • Settings → Billing → History • List of payments: Date, Amount, Plan, Status • 'Download Invoice' (PDF) per transaction • Invoice includes GSTIN (required for Indian businesses) | P2 – Should Have | All | 4 | Not Started | Intern
PAY-05 | Payments & Subscriptions | As a subscribed user, I want to cancel my subscription from within the app. | • Settings → Billing → Cancel Subscription • Confirmation modal explaining what they'll lose • On confirm → calls Razorpay cancel API • Plan remains active until end of billing period • Confirmation email sent • Can re-subscribe at any time | P2 – Should Have | All | 3 | Not Started | Intern
PAY-06 | Payments & Subscriptions | As a free user, I want a clear prompt to upgrade when I hit my usage limit. | • Modal appears when free limit is reached (e.g. 5 scripts/month) • Explains what's included in Pro • 'Upgrade Now' CTA • 'Maybe Later' dismisses • Counter visible on Generate page: 'X of 5 used' | P1 – Must Have | All | 3 | Not Started | Intern
PAY-07 | Payments & Subscriptions | As a user, I want to receive a payment receipt by email. | • Email sent automatically on successful payment • Contains: Plan name, Amount, Invoice number, Date, Support link • Sent from noreply@nuove.in • GST invoice attached as PDF | P1 – Must Have | All | 3 | Not Started | Intern
PAY-08 | Payments & Subscriptions | As a subscribed user, I want to receive a reminder before my subscription renews. | • Email sent 3 days before renewal date • Contains: Amount, Date, 'Manage Subscription' link • Push notification also sent (if enabled) • If payment method will expire → extra warning email | P2 – Should Have | All | 2 | Not Started | Intern
PAY-09 | Payments & Subscriptions | As a user, I want to be able to use a promo/referral code for a discount. | • Promo code field in checkout • Backend validates code → applies discount • Shows: 'Code applied! 30% off' • Codes have expiry date and usage limit • Invalid code shows 'Invalid or expired code' | P3 – Nice to Have | All | 4 | Not Started | Intern
PAY-10 | Payments & Subscriptions | As a subscribed user on iOS, I want to subscribe via Apple In-App Purchase. | • Apple requires IAP for subscriptions sold via iOS app (their rule) • Implement StoreKit 2 via Capacitor plugin • Plan pricing must match equivalent Razorpay pricing (Apple takes 15–30%) • Apple subscription and Razorpay subscription must sync to same user plan • NOTE: This is complex — do this after initial launch | P3 – Nice to Have | iOS | 8 | Not Started | Intern
PAY-11 | Payments & Subscriptions | As a user on Android, I want to subscribe via Google Play Billing. | • Google requires Play Billing for in-app purchases sold via Play Store • Implement via Capacitor Purchases plugin • Sync Google subscription status to backend • NOTE: Like Apple IAP — do after initial launch | P3 – Nice to Have | Android | 8 | Not Started | Intern
▸ NOTIFICATIONS & EMAIL
NOTIF-01 | Notifications & Email | As a new user, I want to receive a welcome email after signing up. | • Email sent within 60 seconds of signup • Subject: 'Welcome to Nuove 🎬' • Contains: User's name, Quick start guide, Link to Dashboard • HTML email with brand colours • Does NOT land in spam (SPF/DKIM configured for nuove.in) | P1 – Must Have | All | 3 | Not Started | Intern
NOTIF-02 | Notifications & Email | As a user, I want to receive a weekly content tip email. | • Sent every Monday at 9 AM IST • One actionable tip related to user's niche • 'Generate a script now' CTA button in email • Unsubscribe link at bottom (required by law) • Sent via Resend.com or SendGrid | P3 – Nice to Have | All | 4 | Not Started | Intern
NOTIF-03 | Notifications & Email | As a user, I want to receive an email when a new feature is released. | • Feature announcement email template • Sent to all active users • Includes GIF/screenshot of new feature • 'Try it now' CTA • Unsubscribe option | P3 – Nice to Have | All | 2 | Not Started | Intern
NOTIF-04 | Notifications & Email | As a mobile user, I want to receive push notifications for important updates. | • Request push permission after user generates first script • Notifications: 'Your weekly tip is ready!', payment reminders, streak alerts • Push via Firebase Cloud Messaging (FCM) • Works on Android (native) and iOS (via Capacitor) • User can disable in Settings | P2 – Should Have | iOS, Android | 5 | Not Started | Intern
NOTIF-05 | Notifications & Email | As a user, I want in-app notifications for key events. | • Bell icon in top nav shows unread count badge • Notification types: Script saved, Payment received, Streak milestone, New feature • Tap notification → navigates to relevant screen • Mark all as read button • Notifications stored in DB (persist across sessions) | P3 – Nice to Have | All | 4 | Not Started | Intern
NOTIF-06 | Notifications & Email | As a user, I want a streak notification if I haven't opened the app in 2 days. | • Push notification after 48h of no activity: 'Your streak is at risk!' • Shown only if user had a streak > 2 days • Sent at 6 PM IST (prime mobile usage time in India) • Can disable in notification settings | P4 – Future | iOS, Android | 3 | Not Started | Intern
▸ MOBILE APP
MOB-01 | Mobile App | As a user, I want the app wrapped as a native iOS app for App Store submission. | • Use Capacitor to wrap the React/Vite app • App opens in fullscreen (no browser chrome) • iOS minimum target: iOS 15 • App icons: all required sizes (20x20 to 1024x1024) • App name: 'Nuove' • Bundle ID: in.nuove.app • Passes Apple App Review Guidelines | P1 – Must Have | iOS | 8 | Not Started | Intern
MOB-02 | Mobile App | As a user, I want the app wrapped as a native Android app for Play Store. | • Use Capacitor for Android build • Android minimum target: API 26 (Android 8) • App icons: all required densities • Package name: in.nuove.app • Signed APK / AAB for Play Store • Passes Google Play policies | P1 – Must Have | Android | 8 | Not Started | Intern
MOB-03 | Mobile App | As a mobile user, I want the app to look correct on all screen sizes. | • Test on: iPhone SE (375px), iPhone 14 (390px), iPhone 14 Pro Max (430px) • Test on: Samsung Galaxy A series (360px wide), Pixel (412px) • No horizontal scrolling on any page • No text overflow or clipping • Bottom nav is thumb-friendly (min 56px height, min 44px tap target) | P1 – Must Have | iOS, Android | 6 | Not Started | Intern
MOB-04 | Mobile App | As a mobile user, I want the app to handle soft keyboard without breaking the layout. | • When soft keyboard opens, layout adjusts correctly • Input fields scroll above keyboard (not hidden behind it) • Use window.visualViewport API to detect keyboard height • Test on iOS Safari and Android Chrome • Modal forms do not get stuck behind keyboard | P1 – Must Have | iOS, Android | 4 | Not Started | Intern
MOB-05 | Mobile App | As a mobile user, I want proper permission dialogs for camera and microphone. | • First launch → native permission dialog (Capacitor handles this) • If denied → show in-app guide: 'Go to Settings → Nuove → Allow Camera' • Include a screenshot/illustration of settings location • Permission check on every entry to Record page • Graceful degradation if mic denied (record video only with no audio) | P1 – Must Have | iOS, Android | 4 | Not Started | Intern
MOB-06 | Mobile App | As an iOS user, I want to save my recording directly to Photos. | • After recording, offer 'Save to Photos' in addition to Download • Uses Capacitor Filesystem + Photos plugin • Requests photo library write permission • Success toast: 'Saved to Photos!' | P2 – Should Have | iOS | 3 | Not Started | Intern
MOB-07 | Mobile App | As a mobile user, I want the app to work when I switch between apps (background/foreground). | • App state preserved when backgrounded • If recording is active and user backgrounds app → pause recording + show alert on return • Session token not lost on backgrounding • Teleprompter position remembered on return | P2 – Should Have | iOS, Android | 4 | Not Started | Intern
MOB-08 | Mobile App | As a user, I want the app to load fast on mobile (including slow 4G). | • Time to Interactive < 3 seconds on 4G • React.lazy() used for all page components • Total JS bundle < 300KB gzipped • Images in WebP format • Fonts preloaded in <head> | P1 – Must Have | iOS, Android | 5 | Not Started | Intern
MOB-09 | Mobile App | As a user, I want smooth animations on mobile (no jank). | • All animations run at 60fps on mid-range Android (2GB RAM) • Avoid animating layout properties (width/height) — use transform/opacity only • Reduce motion respected (prefers-reduced-motion media query) • No animation flicker on page transitions | P2 – Should Have | iOS, Android | 3 | Not Started | Intern
MOB-10 | Mobile App | As a user, I want the app to be submittable to App Store and Play Store. | APP STORE requirements: • Privacy Policy URL in App Store Connect • App Store screenshots: 6.5" and 5.5" iPhone sizes • App description (170 char subtitle + full description) • Age rating: 4+ • No use of private APIs • Apple Sign In implemented (AUTH-03) PLAY STORE requirements: • Feature graphic (1024x500px) • 2 screenshots minimum per device type • Data safety section completed • Target API 33+ (Android 13) | P1 – Must Have | iOS, Android | 6 | Not Started | Intern
MOB-11 | Mobile App | As a user, I want the app icon and splash screen to match the Nuove brand. | • App icon: Nuove clapperboard logo on gradient background • No text in icon (Apple guideline) • Splash screen: brand gradient + Nuove wordmark centred • Splash auto-hides after 1.5 seconds • Dark/light mode app icon variants | P1 – Must Have | iOS, Android | 3 | Not Started | Intern
MOB-12 | Mobile App | As an Android user, I want to install the app via a direct APK link if Play Store review is pending. | • Build signed APK • Host on nuove.in/download/nuove.apk • Landing page with QR code for easy download • Note: This is for beta testing only. Production uses Play Store. | P2 – Should Have | Android | 2 | Not Started | Intern
▸ INFRASTRUCTURE
INFRA-01 | Infrastructure | As the product owner, I want the backend hosted on a paid Railway plan so it never sleeps. | • Upgrade Railway from trial → Hobby ($5/mo) or Pro • Backend responds in < 500ms (no cold start delay) • Health check endpoint: GET /health returns 200 • Railway auto-restarts on crash • FRONTEND_URL env var set to https://nuove.in | P1 – Must Have | All | 1 | Not Started | Intern
INFRA-02 | Infrastructure | As the product owner, I want a PostgreSQL database storing all user data. | • Add Railway PostgreSQL plugin OR use Supabase free tier • Tables: users, scripts, recordings_meta, subscriptions, payments, notifications • DATABASE_URL set in Railway env vars • DB backups enabled (daily minimum) • Connection pooling configured (PgBouncer or pg pool) | P1 – Must Have | All | 5 | Not Started | Intern
INFRA-03 | Infrastructure | As the product owner, I want all app secrets in environment variables, not in code. | • Audit: no API keys in any committed file • Railway env vars: DATABASE_URL, JWT_SECRET, ANTHROPIC_API_KEY, RAZORPAY keys, RESEND key • Vercel env vars: VITE_API_URL • .env.example updated with correct placeholders • Run npm audit — 0 critical vulnerabilities | P1 – Must Have | All | 2 | Not Started | Intern
INFRA-04 | Infrastructure | As the product owner, I want CI/CD so the app deploys automatically on code push. | • GitHub Actions: run npm test + npm run lint on every PR • Merge to main → auto-deploy to Railway (backend) and Vercel (frontend) • PR blocked from merge if tests fail • Deployment takes < 3 minutes | P2 – Should Have | All | 5 | Not Started | Intern
INFRA-05 | Infrastructure | As the product owner, I want uptime monitoring so I know if the app goes down. | • UptimeRobot (free): ping /health every 5 minutes • Alert via email + Slack if down for > 2 minutes • Also prevents Railway free tier sleep (if still on free) • Public status page (optional): status.nuove.in | P1 – Must Have | All | 1 | Not Started | Intern
INFRA-06 | Infrastructure | As the product owner, I want error tracking to catch bugs in production. | • Sentry.io added to both frontend and backend (free tier) • Source maps uploaded for readable stack traces • Alerts for new errors sent to Slack/email • Errors tagged with userId for faster debugging | P2 – Should Have | All | 4 | Not Started | Intern
INFRA-07 | Infrastructure | As the product owner, I want file storage for user uploads and recordings metadata. | • Cloudflare R2 (free 10GB) or AWS S3 for video/image storage • Videos NOT stored long-term — only metadata stored in DB • Profile photos stored in R2 with public read URL • File size limit: 50MB per upload | P2 – Should Have | All | 4 | Not Started | Intern
INFRA-08 | Infrastructure | As the product owner, I want transactional email working from nuove.in domain. | • Resend.com free tier (3,000 emails/month) • DNS records: SPF, DKIM, DMARC configured for nuove.in • Verify domain in Resend dashboard • Test: send email from noreply@nuove.in → should not land in spam • EMAIL_FROM=Nuove <noreply@nuove.in> | P1 – Must Have | All | 2 | Not Started | Intern
INFRA-09 | Infrastructure | As the product owner, I want the backend CORS configured correctly for nuove.in. | • ALLOWED_ORIGINS in app.js includes: https://nuove.in, https://www.nuove.in • Also allows all *.vercel.app for preview deployments • All API calls from nuove.in return correct CORS headers • No CORS errors in browser console on production | P1 – Must Have | All | 1 | Not Started | Intern
▸ TESTING & QA
TEST-01 | Testing & QA | As the intern, I want a manual QA checklist to test every feature before release. | • Create test cases for: Login, Signup, Generate Script, Save Script, Record, Download, Crosspost, Billing, Settings • Each test case has: Steps to reproduce, Expected result, Pass/Fail column • Run checklist before every production deployment • Document in Notion or Google Sheets | P1 – Must Have | All | 5 | Not Started | Intern
TEST-02 | Testing & QA | As the intern, I want the critical API routes to have automated tests. | • Use Jest + Supertest • Test: POST /auth/signup, POST /auth/login, POST /generate, GET /scripts, POST /payments/webhook • Tests run in CI pipeline • Minimum: happy path + 1 error case per route | P2 – Should Have | All | 8 | Not Started | Intern
TEST-03 | Testing & QA | As the product owner, I want the app tested on real devices before launch. | • Test on: iPhone 12/13/14 (iOS 15, 16, 17) • Test on: Samsung Galaxy A32 / Redmi Note (Android 10, 12) • Test on: iPad (tablet layout acceptable) • Document any device-specific bugs found • All P1 bugs fixed before launch | P1 – Must Have | iOS, Android | 8 | Not Started | Intern
TEST-04 | Testing & QA | As the intern, I want to run Lighthouse and fix performance scores before App Store submission. | • Run Lighthouse on nuove.in on mobile preset • Target scores: Performance > 85, Accessibility > 90, SEO > 90, Best Practices > 90 • Fix all issues flagged as 'Needs Improvement' or 'Poor' • Run in GitHub Actions CI to catch regressions | P2 – Should Have | All | 4 | Not Started | Intern
TEST-05 | Testing & QA | As the intern, I want to test the full payment flow end-to-end. | • Test with Razorpay test cards (4111 1111 1111 1111) • Flow: Click Upgrade → Razorpay opens → Pay → Plan activates • Test payment failure (declined card) • Test subscription cancellation • Test webhook delivery (use Razorpay webhook simulator) • Verify email receipt arrives | P1 – Must Have | All | 5 | Not Started | Intern
TEST-06 | Testing & QA | As the intern, I want to test the recording feature across all major browsers. | • Test on: iOS Safari 15+, iOS Chrome, Android Chrome 90+, Desktop Chrome, Desktop Firefox, Desktop Safari • Camera opens correctly • Recording starts/stops correctly • Downloaded file plays in native player • Document any browser-specific issues | P1 – Must Have | iOS, Android | 5 | Not Started | Intern
TEST-07 | Testing & QA | As the product owner, I want the app to handle network errors gracefully. | • Simulate offline mode (DevTools → Offline) • Each API call failure shows a user-friendly error (not console error) • Retry button shown where applicable • No white screen of death under any network condition • Test slow 3G preset in Chrome DevTools | P2 – Should Have | All | 3 | Not Started | Intern
TEST-08 | Testing & QA | As the intern, I want to run accessibility audit before submission. | • Run axe-core or Lighthouse Accessibility audit on all pages • Fix all 'Critical' and 'Serious' violations • All images have alt text • All form inputs have labels • Minimum contrast ratio 4.5:1 for body text • Keyboard navigation works on all interactive elements | P2 – Should Have | All | 5 | Not Started | Intern
▸ SECURITY
SEC-01 | Security | As the product owner, I want rate limiting on all API routes to prevent abuse. | • Use express-rate-limit • /auth/login: max 5 requests per 15 minutes per IP • /auth/signup: max 3 per hour per IP • /generate: max 10 per minute per user • Returns 429 with message: 'Too many requests. Please wait.' • Prevents AI API cost explosion from abuse | P1 – Must Have | All | 3 | Not Started | Intern
SEC-02 | Security | As the product owner, I want all user inputs validated and sanitised on the backend. | • Use Zod or Joi for schema validation on every POST/PUT route • Validate: email format, password strength, string lengths • Strip HTML tags from text inputs (XSS prevention) • Return 400 with clear error message for invalid input • Never pass unsanitised input to the AI API | P1 – Must Have | All | 4 | Not Started | Intern
SEC-03 | Security | As the product owner, I want security headers on all API responses. | • Use helmet.js middleware • Headers: HSTS, X-Frame-Options, X-Content-Type-Options, Referrer-Policy • No server version headers • CSP configured to allow nuove.in and CDN sources only | P1 – Must Have | All | 2 | Not Started | Intern
SEC-04 | Security | As the product owner, I want Razorpay webhook signature verified before processing. | • Every incoming Razorpay webhook must verify HMAC-SHA256 signature • Use razorpay.webhooks.verify(body, signature, secret) • Reject unverified webhooks with 400 • Log all webhook events • Never process payment without signature verification | P1 – Must Have | All | 2 | Not Started | Intern
SEC-05 | Security | As the product owner, I want no sensitive data exposed in frontend bundle. | • Audit Vite build output — no Anthropic/OpenAI keys in bundle • No Razorpay secret key in frontend • All AI calls go through backend proxy • Environment variables with VITE_ prefix are exposed to frontend — audit all of them | P1 – Must Have | All | 2 | Not Started | Intern
SEC-06 | Security | As the product owner, I want brute-force protection on the login endpoint. | • After 5 failed login attempts: lock account for 15 minutes • Show: 'Account locked. Try again in 15 minutes or reset your password.' • Implemented via per-email attempt counter in DB or Redis • Admin can manually unlock accounts | P1 – Must Have | All | 3 | Not Started | Intern
SEC-07 | Security | As the product owner, I want all dependencies audited for vulnerabilities. | • Run npm audit on both frontend and backend • Fix all HIGH and CRITICAL severity vulnerabilities • Add npm audit to CI pipeline — fail build on HIGH+ • Review before every App Store submission | P2 – Should Have | All | 2 | Not Started | Intern
▸ LEGAL & COMPLIANCE
LEGAL-01 | Legal & Compliance | As the product owner, I need a Terms & Conditions page before accepting payments. | • Route: nuove.in/terms • Covers: usage policy, AI-generated content ownership, refund policy, prohibited use, account termination • Must be live and linked from: signup page, checkout page, Settings → About • Required by Razorpay live account activation • Consult a lawyer or use a reputable SaaS T&C template | P1 – Must Have | All | 3 | Not Started | Intern
LEGAL-02 | Legal & Compliance | As the product owner, I need a Privacy Policy compliant with DPDP Act 2023. | • Route: nuove.in/privacy • Covers: what data is collected, how it's used, storage location, user rights, deletion process • DPDP Act 2023 (India) compliance: user consent, data principal rights • Linked from: signup page, Settings → About • Must state: Nuove does NOT sell user data | P1 – Must Have | All | 3 | Not Started | Intern
LEGAL-03 | Legal & Compliance | As a user, I want to give clear consent to data collection when I sign up. | • Signup page has: checkbox 'I agree to Terms & Conditions and Privacy Policy' • Checkbox is NOT pre-checked • Links open in modal or new tab • Cannot submit form without checking the box • Consent timestamp stored in DB | P1 – Must Have | All | 2 | Not Started | Intern
LEGAL-04 | Legal & Compliance | As the product owner, I need an AI content disclosure visible to users. | • Disclaimer visible on Script Generator output: 'Scripts are AI-generated. Please review before posting.' • Brief statement in T&C about AI-generated content • Does not imply Nuove owns copyright to generated scripts • Required by emerging AI content regulations | P2 – Should Have | All | 1 | Not Started | Intern
LEGAL-05 | Legal & Compliance | As the product owner, I want to register the Nuove trademark and verify GST. | • Check trademark: IP India search for 'Nuove' in Class 9 (software) and Class 42 (SaaS) • File trademark application (~₹4,500) if clear • GSTIN required for Razorpay live account and GST invoices • Register company (Pvt Ltd or LLP) if not already done • This is a business task — involves a CA and lawyer | P1 – Must Have | All | 0 | Not Started | Intern
LEGAL-06 | Legal & Compliance | As the product owner, I want cookie consent for European users. | • Add CookieYes or Cookiebot banner (free tier) • Only essential cookies set before consent • Analytics/marketing cookies only after explicit accept • 'Reject All' option must be equally prominent as 'Accept' • Required for GDPR compliance | P2 – Should Have | All | 2 | Not Started | Intern
▸ PERFORMANCE & ANALYTICS
PERF-01 | Performance & Analytics | As the product owner, I want Google Analytics 4 tracking user behaviour. | • Add GA4 to Vercel project • Track custom events: script_generated, recording_started, recording_completed, subscription_started, subscription_cancelled • Page view tracking automatic • Filter out localhost traffic • Connect GA4 to Google Search Console | P1 – Must Have | All | 3 | Not Started | Intern
PERF-02 | Performance & Analytics | As the product owner, I want to see where users drop off in the product funnel. | • Define funnel in GA4 or Posthog: Signup → Generate Script → Save Script → Record → Share/Crosspost → Subscribe • Weekly review of funnel drop-off rates • Alert if conversion rate drops > 20% week-over-week | P2 – Should Have | All | 3 | Not Started | Intern
PERF-03 | Performance & Analytics | As the product owner, I want Hotjar or Microsoft Clarity for session recordings. | • Microsoft Clarity (free, no data limit) • Heatmaps on: Dashboard, Generate, Record, Pricing pages • Session recordings enabled • Review weekly to find UX problems • Add after launch (not needed pre-launch) | P3 – Nice to Have | All | 2 | Not Started | Intern
PERF-04 | Performance & Analytics | As the product owner, I want the frontend bundle optimised for fast mobile load. | • React.lazy() + Suspense for all page-level components • Run: npx vite-bundle-analyzer • Remove unused imports • Replace moment.js with dayjs (10x smaller) • Total bundle: < 300KB gzipped • First Contentful Paint < 1.5s on 4G | P1 – Must Have | All | 4 | Not Started | Intern
PERF-05 | Performance & Analytics | As the product owner, I want AI responses to stream instead of waiting for full response. | • Use Anthropic streaming API • Frontend renders text word-by-word as it arrives • Shows spinner only for first 500ms, then text starts appearing • User perceives faster response even if total time is same • Implement in /generate endpoint | P2 – Should Have | All | 5 | Not Started | Intern
PERF-06 | Performance & Analytics | As the product owner, I want a public landing page to drive organic signups. | • Route: nuove.in (before login redirect) • Sections: Hero, Features, How it works, Pricing, Testimonials, CTA • SEO meta tags: title, description, og:image, og:title • Mobile-first design • Page load < 2s • 'Get Started Free' CTA → signup page | P1 – Must Have | All | 10 | Not Started | Intern
PERF-07 | Performance & Analytics | As the product owner, I want sitemap.xml and robots.txt for SEO. | • /sitemap.xml lists all public pages (landing, features, pricing, terms, privacy) • /robots.txt allows all crawlers on public pages, disallows /api and /dashboard • Submit sitemap to Google Search Console • Add canonical tags to prevent duplicate content | P2 – Should Have | All | 2 | Not Started | Intern

## Sprint Plan
NUOVE — SUGGESTED SPRINT PLAN (8 WEEKS TO APP STORE)
Each sprint = 1 week. Complete all P1 items before submitting to App Store / Play Store.
Sprint | Theme | Stories to Complete | Definition of Done | Est. Hours
Sprint 1 Week 1 | Infrastructure & Auth | • INFRA-01: Upgrade Railway to paid • INFRA-02: Set up PostgreSQL • INFRA-03: Secure all env vars • INFRA-08: Email service (Resend + nuove.in DNS) • AUTH-01: Email/password signup + login • AUTH-04: JWT + refresh tokens • AUTH-05: Forgot password flow | Backend live with DB. Users can sign up and log in. | 35
Sprint 2 Week 2 | Core Features (Script + History) | • AUTH-02: Google OAuth • AUTH-06: Onboarding flow • GEN-01 to GEN-06: Full script generator • HIST-01 to HIST-03: Script history (save/load/delete) • INFRA-05: UptimeRobot monitoring | Users can generate, save and view scripts. | 38
Sprint 3 Week 3 | Recorder + Crosspost | • REC-01 to REC-06: Teleprompter & recorder (web) • REC-07: iOS codec fix • CROSS-01 to CROSS-04: Crosspost with captions • SEC-01 to SEC-06: Rate limiting + security headers | Core features all working on web. | 40
Sprint 4 Week 4 | Payments | • PAY-01: Pricing page • PAY-02 to PAY-03: Razorpay live + webhook • PAY-04: Billing history • PAY-05: Cancel subscription • PAY-06: Free tier limits • PAY-07 to PAY-08: Payment emails • TEST-05: End-to-end payment QA | Users can subscribe and pay. Revenue can be earned. | 44
Sprint 5 Week 5 | Legal + Landing Page | • LEGAL-01: Terms & Conditions live • LEGAL-02: Privacy Policy live • LEGAL-03: Consent checkbox on signup • LEGAL-04: AI content disclosure • LEGAL-05: GST/company registration (parallel, external) • PERF-06: Public landing page • PERF-07: Sitemap + robots.txt • PERF-01: Google Analytics 4 | App is legally compliant. Public landing page live. | 25
Sprint 6 Week 6 | Mobile App Build | • AUTH-03: Apple Sign In • AUTH-07: Splash screen • MOB-01: Capacitor iOS build • MOB-02: Capacitor Android build • MOB-03 to MOB-05: Mobile layout + permissions • MOB-08: Performance optimisation • MOB-10: App Store + Play Store assets | Native apps built and running on real devices. | 42
Sprint 7 Week 7 | QA + Bug Fixes | • TEST-01: Manual QA checklist run • TEST-03: Real device testing (iPhone + Samsung) • TEST-04: Lighthouse scores • TEST-06: Cross-browser recording test • TEST-07: Network error handling • TEST-08: Accessibility audit • Fix all P1 bugs found | All P1 and P2 bugs fixed. App ready for submission. | 36
Sprint 8 Week 8 | App Store Submission | • MOB-11: Final app icons + splash screens • MOB-10: Submit to Apple App Store (review: 1–3 days) • MOB-02: Submit to Google Play Store (review: 1–7 days) • NOTIF-01: Welcome email live • PROF-01 to PROF-06: Profile + settings complete • INFRA-04: CI/CD pipeline • Monitor: Sentry + Railway logs | App submitted to both stores. 🚀 | 30