## 📋 Summary
Nuove – Production Readiness Tracker
Prepared for: Junior Developer Handoff ¦ Prepared by: Senior Product Head ¦ App: Nuove (AI Reel Coach)
PRIORITY LEGEND
P1 – Critical |  | Must be done BEFORE launch. Blocking.
P2 – High |  | Do within first 2 weeks of launch.
P3 – Medium |  | Important – schedule within Month 1.
P4 – Low |  | Nice-to-have or post-Month-1.
CATEGORY SUMMARY
Category | Total Tasks | P1 | P2 | P3 | P4 | Est. Hours | Owner
1. Infrastructure & DevOps | 8 | 3 | 3 | 2 | 0 | 24 | Junior Dev
2. Payments & Billing | 10 | 4 | 4 | 2 | 0 | 40 | Junior Dev
3. Mobile Readiness | 14 | 4 | 5 | 4 | 1 | 50 | Junior Dev
4. Security | 10 | 5 | 3 | 2 | 0 | 30 | Junior Dev
5. Feature Completion | 12 | 3 | 5 | 3 | 1 | 55 | Junior Dev
6. Testing & QA | 11 | 3 | 4 | 3 | 1 | 38 | Junior Dev
7. UI / UX Polish | 9 | 2 | 3 | 3 | 1 | 28 | Junior Dev
8. Analytics & Monitoring | 7 | 2 | 3 | 2 | 0 | 20 | Junior Dev
9. Email & Notifications | 6 | 2 | 2 | 2 | 0 | 16 | Junior Dev
10. Performance | 7 | 2 | 3 | 2 | 0 | 22 | Junior Dev
11. SEO & Social Meta | 5 | 1 | 2 | 2 | 0 | 10 | Junior Dev
12. Legal & Compliance | 6 | 3 | 2 | 1 | 0 | 18 | Junior Dev
13. Accessibility | 5 | 1 | 2 | 2 | 0 | 12 | Junior Dev
14. PWA & Offline | 5 | 1 | 2 | 1 | 1 | 15 | Junior Dev
TOTAL | 115 | 36 | 43 | 31 | 5 | 378
KEY INFRASTRUCTURE DECISIONS
Component | Current | Recommendation / Action Required
Frontend Hosting | Vercel | ✅ Fine for production. Enable Analytics, set custom domain, configure rate-limit headers.
Backend Hosting | Railway | ⚠️ Free tier sleeps after 5 min inactivity – causes cold starts. Upgrade to Hobby ($5/mo) or Starter plan before launch.
Database | TBD | ❗ Not confirmed. Add PostgreSQL or MongoDB (Railway add-on or Atlas free tier). Required for users, scripts, payments.
File Storage | TBD | ❗ For recorded videos & uploads use Cloudflare R2 (free 10GB) or AWS S3.
CDN | Vercel Edge | ✅ Vercel handles CDN automatically for frontend assets.
Email | TBD | ❗ Add Resend.com or SendGrid free tier for transactional emails (OTP, receipts).
Payments | Razorpay | ⚠️ Only test keys configured. Need live keys + webhook + GST details + T&C page before charging users.

## 📝 All Tasks
Nuove – Full Task List (115 Tasks)
# | Category | Task | Details / Acceptance Criteria | Priority | Est. Hrs | Status | Assigned To | Notes
1 | Infrastructure & DevOps | Upgrade Railway to paid plan | Free tier sleeps after 5 min. Upgrade to Hobby ($5/mo). Eliminates cold-start delays for real users. | P1 – Critical | 1 | Not Started | Junior Dev
2 | Infrastructure & DevOps | Add PostgreSQL database | Railway PostgreSQL add-on OR Supabase free tier. Schema: users, scripts, sessions, payments, subscriptions. | P1 – Critical | 3 | Not Started | Junior Dev
3 | Infrastructure & DevOps | Configure custom domain on Vercel | Point nuove.in (or .com) to Vercel deployment. Enable HTTPS auto-cert. Update CORS origins on backend. | P1 – Critical | 2 | Not Started | Junior Dev
4 | Infrastructure & DevOps | Set environment variables in prod | Move all secrets (API keys, DB URLs, JWT secret, Razorpay keys) to Railway + Vercel env vars. No secrets in code. | P2 – High | 2 | Not Started | Junior Dev
5 | Infrastructure & DevOps | Set up CI/CD pipeline | GitHub Actions: run lint + tests on PR, auto-deploy main to Railway+Vercel on merge. Fail fast on broken builds. | P2 – High | 4 | Not Started | Junior Dev
6 | Infrastructure & DevOps | Configure backend health-check endpoint | GET /health returns 200 + uptime. Railway uses this to monitor. Prevents Railway from killing the dyno. | P2 – High | 1 | Not Started | Junior Dev
7 | Infrastructure & DevOps | Set up error tracking (Sentry) | Add Sentry SDK to both frontend and backend. Configure source maps. Set up Slack/email alerts for P1 errors. | P3 – Medium | 4 | Not Started | Junior Dev
8 | Infrastructure & DevOps | Configure log aggregation | Use Railway's built-in logs + Logtail (free tier). Tag logs with userId and route for debugging. | P3 – Medium | 3 | Not Started | Junior Dev
9 | Payments & Billing | Switch Razorpay to live keys | Replace test key_id/key_secret with live credentials. Test end-to-end with ₹1 transaction before launch. | P1 – Critical | 2 | Not Started | Junior Dev
10 | Payments & Billing | Build subscription plans UI | Show Free / Pro (₹X/mo) / Creator (₹X/mo) tiers with feature comparison table. Match brand design. | P1 – Critical | 6 | Not Started | Junior Dev
11 | Payments & Billing | Implement Razorpay webhook handler | Verify webhook signature. Handle: payment.captured, subscription.activated, subscription.cancelled, payment.failed. | P1 – Critical | 4 | Not Started | Junior Dev
12 | Payments & Billing | Store subscription state in DB | Users table: plan, subscription_id, subscription_status, next_billing_date. Gate features on plan. | P1 – Critical | 3 | Not Started | Junior Dev
13 | Payments & Billing | Build billing history page | Show past invoices, next billing date, plan details. Allow cancel/upgrade from UI. | P2 – High | 5 | Not Started | Junior Dev
14 | Payments & Billing | Add GST invoice generation | Indian law requires GST invoices. Integrate Razorpay's invoice API or generate PDF with company GSTIN. | P2 – High | 4 | Not Started | Junior Dev
15 | Payments & Billing | Implement free-tier usage limits | Cap free users: e.g. 5 scripts/month, 3 recordings/month. Show upgrade prompt when limit hit. | P2 – High | 4 | Not Started | Junior Dev
16 | Payments & Billing | Add promo code / coupon support | Razorpay supports discount codes. Build UI field + backend validation. For early-bird and influencer campaigns. | P2 – High | 3 | Not Started | Junior Dev
17 | Payments & Billing | Handle payment failure gracefully | Show clear error message, don't lock user out immediately. Retry flow + email reminder. | P3 – Medium | 3 | Not Started | Junior Dev
18 | Payments & Billing | Refund & cancellation flow | Admin panel or support email flow for refund requests. Razorpay refund API. Document policy in T&C. | P3 – Medium | 5 | Not Started | Junior Dev
19 | Mobile Readiness | Audit all pages on 375px viewport | Check every page on iPhone SE size. Fix overflows, unreadable text, broken layouts. Primary audience is mobile. | P1 – Critical | 4 | Not Started | Junior Dev
20 | Mobile Readiness | Fix camera/recorder on iOS Safari | getUserMedia + MediaRecorder behaves differently on iOS. Test recording + playback. Handle codec differences (webm vs mp4). | P1 – Critical | 6 | Not Started | Junior Dev
21 | Mobile Readiness | Fix teleprompter scroll on touch devices | Touch-scroll interferes with auto-scroll. Disable native scroll during recording. Test on Android Chrome + iOS Safari. | P1 – Critical | 3 | Not Started | Junior Dev
22 | Mobile Readiness | Test navigation on mobile (bottom nav) | Bottom nav bar must be thumb-friendly (min 48px tap targets). Check active states, icons, labels. | P1 – Critical | 2 | Not Started | Junior Dev
23 | Mobile Readiness | Fix keyboard push-up layout on mobile | When soft keyboard opens, it can break layouts. Use visual-viewport API to handle keyboard height. | P2 – High | 4 | Not Started | Junior Dev
24 | Mobile Readiness | Test Crosspost page on mobile | Social platform buttons must be full-width and readable. Caption text area must resize correctly. | P2 – High | 2 | Not Started | Junior Dev
25 | Mobile Readiness | Test Generate page on mobile | Dropdowns, tone selectors, script output card must all work on small screen. | P2 – High | 2 | Not Started | Junior Dev
26 | Mobile Readiness | Test Script History on mobile | List items must be readable. Edit/delete actions accessible without hover. | P2 – High | 2 | Not Started | Junior Dev
27 | Mobile Readiness | Add mobile-specific touch gestures | Swipe to dismiss modals. Pull-to-refresh on script history. Standard mobile UX patterns. | P3 – Medium | 4 | Not Started | Junior Dev
28 | Mobile Readiness | Optimize images for mobile | All images served in WebP. Responsive srcset. No uncompressed PNGs. Reduces data usage for Indian mobile users. | P3 – Medium | 3 | Not Started | Junior Dev
29 | Mobile Readiness | Test on actual Android devices | Test on low-end Android (2GB RAM, Chrome). Check performance, animations, font rendering. | P3 – Medium | 3 | Not Started | Junior Dev
30 | Mobile Readiness | Test on actual iOS devices | Test on iPhone (Safari). Check recording, playback, all interactions. | P3 – Medium | 3 | Not Started | Junior Dev
31 | Mobile Readiness | Add haptic feedback (vibration API) | Light vibration on record start/stop. Improves perceived quality on mobile. | P4 – Low | 2 | Not Started | Junior Dev
32 | Mobile Readiness | Consider React Native or Capacitor | Long-term: a native app gets push notifications, better camera access. Evaluate after web is stable. | P4 – Low | 0 | Not Started | Junior Dev
33 | Security | Implement JWT auth with refresh tokens | Current auth may use short-lived tokens only. Add refresh token rotation. Store refresh token in httpOnly cookie. | P1 – Critical | 5 | Not Started | Junior Dev
34 | Security | Add rate limiting to all API routes | Use express-rate-limit. Limits: /generate: 10/min, /auth: 5/min, /record: 20/min. Prevents abuse and AI API cost explosion. | P1 – Critical | 3 | Not Started | Junior Dev
35 | Security | Validate and sanitize all user inputs | Use Zod or Joi for input validation on every backend route. Prevents injection attacks. | P1 – Critical | 4 | Not Started | Junior Dev
36 | Security | Add HTTPS-only headers | Helmet.js: HSTS, X-Frame-Options, CSP, X-Content-Type-Options. 1-line setup protects from common attacks. | P1 – Critical | 1 | Not Started | Junior Dev
37 | Security | Protect AI API keys from front-end exposure | Confirm no Anthropic/OpenAI keys are in frontend bundle. All AI calls must be server-side only. | P1 – Critical | 2 | Not Started | Junior Dev
38 | Security | Implement CORS whitelist | Only allow requests from your Vercel domain + localhost. Currently may be open to all origins. | P2 – High | 1 | Not Started | Junior Dev
39 | Security | Add brute-force protection on login | Lockout after 5 failed attempts. Implement with express-rate-limit or a per-user attempt counter in Redis/DB. | P2 – High | 3 | Not Started | Junior Dev
40 | Security | Encrypt sensitive data at rest | User PII (email, name) should be stored with encryption or at minimum with a DB with encryption-at-rest enabled. | P2 – High | 3 | Not Started | Junior Dev
41 | Security | Security audit of dependencies | Run `npm audit` on both frontend and backend. Fix all high/critical vulnerabilities. Add to CI/CD pipeline. | P3 – Medium | 2 | Not Started | Junior Dev
42 | Security | Add 2FA (optional but recommended) | Optional TOTP (Google Authenticator) for Pro users. Adds trust signal for subscription tier. | P3 – Medium | 6 | Not Started | Junior Dev
43 | Feature Completion | Complete user onboarding flow | After signup: niche selection, language preference, sample script generation. First-run experience is critical for activation. | P1 – Critical | 6 | Not Started | Junior Dev
44 | Feature Completion | Build user settings page | Change name, email, password, language preference, notification preferences. Currently missing or incomplete. | P1 – Critical | 4 | Not Started | Junior Dev
45 | Feature Completion | Complete script save/load flow | Scripts saved to DB (not just localStorage). Associate scripts with user ID. Load on Scripts History page. | P1 – Critical | 5 | Not Started | Junior Dev
46 | Feature Completion | Integrate real social auth (Google/Apple) | Currently may use email/password only. Google OAuth = fewer drop-offs. Apple required for iOS App Store. | P2 – High | 5 | Not Started | Junior Dev
47 | Feature Completion | Build admin dashboard | View user count, active subscriptions, revenue, error logs. Minimum: read-only data view. Use Retool or build simple page. | P2 – High | 8 | Not Started | Junior Dev
48 | Feature Completion | Add notification system | In-app notifications: script generated, subscription reminder, new feature alert. Badge count on bell icon. | P2 – High | 5 | Not Started | Junior Dev
49 | Feature Completion | Implement script sharing | User can share script via link (read-only public URL). Good for viral growth. | P2 – High | 4 | Not Started | Junior Dev
50 | Feature Completion | Add multi-language caption generation | Language selector in caption section works end-to-end. Supports at least: English, Hindi, Hinglish, Tamil, Telugu. | P2 – High | 3 | Not Started | Junior Dev
51 | Feature Completion | Complete Profile page | Show script count, recording count, streak, joined date. Edit avatar/profile photo upload. | P3 – Medium | 4 | Not Started | Junior Dev
52 | Feature Completion | Build FAQ / Help page | Simple static FAQ. Reduces support load. Answer top 10 questions: billing, recording, formats, etc. | P3 – Medium | 3 | Not Started | Junior Dev
53 | Feature Completion | Add feedback / bug report button | Floating button on all pages. Submits to Airtable, Notion, or email. Free tools available. | P3 – Medium | 2 | Not Started | Junior Dev
54 | Feature Completion | Build Creator Dashboard widgets | Weekly stats: scripts written, recordings made, streak. Show trend line. Motivates continued use. | P4 – Low | 5 | Not Started | Junior Dev
55 | Testing & QA | Write unit tests for backend API routes | Use Jest + Supertest. Test: /generate, /auth, /scripts, /payments. Min 70% coverage on critical paths. | P1 – Critical | 8 | Not Started | Junior Dev
56 | Testing & QA | Write integration tests for payment flow | End-to-end test with Razorpay test mode: subscribe → webhook → feature unlock → cancel → feature lock. | P1 – Critical | 5 | Not Started | Junior Dev
57 | Testing & QA | Set up automated test runner in CI | GitHub Actions runs all tests on every PR. Merge blocked if tests fail. Prevents regressions. | P1 – Critical | 3 | Not Started | Junior Dev
58 | Testing & QA | Manual QA test plan document | Document step-by-step test cases for all features. Junior dev runs through before each release. | P2 – High | 4 | Not Started | Junior Dev
59 | Testing & QA | Cross-browser testing | Test on: Chrome, Firefox, Safari (macOS), Safari (iOS), Chrome (Android). Note and fix differences. | P2 – High | 4 | Not Started | Junior Dev
60 | Testing & QA | Performance testing | Use Lighthouse CI in GitHub Actions. Target: Performance >85, Accessibility >90, SEO >90 on mobile. | P2 – High | 3 | Not Started | Junior Dev
61 | Testing & QA | Load testing on backend | Use k6 or Artillery. Simulate 100 concurrent users hitting /generate. Identify breaking point. Railway Hobby handles ~50 req/s. | P3 – Medium | 4 | Not Started | Junior Dev
62 | Testing & QA | Accessibility testing | Run axe-core on all pages. Fix all critical and serious violations. WCAG 2.1 AA minimum. | P3 – Medium | 4 | Not Started | Junior Dev
63 | Testing & QA | User acceptance testing (UAT) | Recruit 5 beta users (real content creators). Give them tasks. Record session with Hotjar. Fix top 3 pain points. | P3 – Medium | 6 | Not Started | Junior Dev
64 | Testing & QA | Error boundary testing | Deliberately break API calls. Confirm error boundaries show friendly messages, not white screen of death. | P4 – Low | 2 | Not Started | Junior Dev
65 | Testing & QA | Visual regression testing | Add Percy or Chromatic for visual diff on key pages. Prevents unintended UI regressions. | P4 – Low | 4 | Not Started | Junior Dev
66 | UI / UX Polish | Add loading states to all async actions | Every button that triggers an API call must show a spinner and be disabled while pending. No double-submit. | P1 – Critical | 4 | Not Started | Junior Dev
67 | UI / UX Polish | Add empty states to all list pages | Script History empty: 'No scripts yet. Generate your first one!' with a CTA button. Same for other lists. | P2 – High | 3 | Not Started | Junior Dev
68 | UI / UX Polish | Toast / notification system | Global toast for: ✓ Script saved, ✗ Error generating, ✓ Copied to clipboard. Use react-hot-toast. | P2 – High | 2 | Not Started | Junior Dev
69 | UI / UX Polish | Add skeleton loaders | Replace blank screens during load with skeleton UI (pulsing grey blocks). Improves perceived performance. | P2 – High | 3 | Not Started | Junior Dev
70 | UI / UX Polish | Confirm destructive actions | Delete script, cancel subscription: show modal 'Are you sure?' Prevents accidental data loss. | P3 – Medium | 2 | Not Started | Junior Dev
71 | UI / UX Polish | Add onboarding tooltips / coach marks | First-time user sees highlighted tips on key features. Use react-joyride or shepherd.js. | P3 – Medium | 4 | Not Started | Junior Dev
72 | UI / UX Polish | Keyboard accessibility | All interactive elements reachable by Tab. Enter/Space activates buttons. Esc closes modals. | P3 – Medium | 4 | Not Started | Junior Dev
73 | UI / UX Polish | Dark mode polish | Audit all pages in dark mode. Fix any hard-coded light colours that look broken. Gradient text must be visible. | P3 – Medium | 3 | Not Started | Junior Dev
74 | UI / UX Polish | Micro-animation audit | Review all page transitions and button interactions. Remove janky ones. Ensure consistent 200ms ease-out. | P4 – Low | 3 | Not Started | Junior Dev
75 | Analytics & Monitoring | Add Vercel Analytics | Enable Vercel's built-in Web Analytics. Free. Shows page views, top pages, countries. | P1 – Critical | 1 | Not Started | Junior Dev
76 | Analytics & Monitoring | Set up Google Analytics 4 or Posthog | Track custom events: script_generated, recording_started, recording_completed, subscription_started. | P1 – Critical | 3 | Not Started | Junior Dev
77 | Analytics & Monitoring | Add uptime monitoring | Use UptimeRobot (free). Ping /health every 5 min. Alert on Slack/email if down. Prevents Railway sleep on free tier. | P2 – High | 1 | Not Started | Junior Dev
78 | Analytics & Monitoring | Track funnel metrics | Define funnel: signup → generate script → record → share. Measure drop-off at each step. | P2 – High | 3 | Not Started | Junior Dev
79 | Analytics & Monitoring | Add Hotjar or Microsoft Clarity | Session recordings + heatmaps. Free tier is sufficient. Shows exactly where users are confused. | P2 – High | 2 | Not Started | Junior Dev
80 | Analytics & Monitoring | Build revenue dashboard | Track MRR, churn rate, new subscriptions per day. Can use Razorpay dashboard + manual spreadsheet initially. | P3 – Medium | 4 | Not Started | Junior Dev
81 | Analytics & Monitoring | Set up alerting thresholds | Alert if: error rate >1%, API latency >2s, new signups drop to 0 for 24h. Use Sentry + UptimeRobot. | P3 – Medium | 3 | Not Started | Junior Dev
82 | Email & Notifications | Set up transactional email (Resend or SendGrid) | Choose provider. Add DNS records (SPF, DKIM). Prevents emails landing in spam. | P1 – Critical | 2 | Not Started | Junior Dev
83 | Email & Notifications | Welcome email on signup | Triggered on new user creation. Include: app overview, top 3 features, link to first action. | P1 – Critical | 2 | Not Started | Junior Dev
84 | Email & Notifications | Payment receipt email | Triggered on successful payment. Include: plan, amount, invoice link, support email. | P2 – High | 2 | Not Started | Junior Dev
85 | Email & Notifications | Subscription renewal reminder | Email 3 days before renewal. Include: amount, cancel link, upgrade option. | P2 – High | 2 | Not Started | Junior Dev
86 | Email & Notifications | Weekly engagement email | 7-day summary: scripts written, streak. 'You wrote X scripts this week!' Drives retention. | P3 – Medium | 4 | Not Started | Junior Dev
87 | Email & Notifications | Password reset email | Standard forgot-password flow. Secure token, 1-hour expiry. Test on all major email clients. | P3 – Medium | 3 | Not Started | Junior Dev
88 | Performance | Lazy-load route components | Use React.lazy() + Suspense for all page components. Reduces initial bundle size. Critical for mobile 4G. | P1 – Critical | 2 | Not Started | Junior Dev
89 | Performance | Audit and reduce JavaScript bundle size | Run `npx vite-bundle-analyzer`. Remove unused imports. Split large libraries (e.g. moment.js → dayjs). | P1 – Critical | 4 | Not Started | Junior Dev
90 | Performance | Optimise AI API response time | Stream responses from AI backend instead of waiting for full response. Users see text appear progressively. | P2 – High | 5 | Not Started | Junior Dev
91 | Performance | Add Redis caching for repeated AI queries | Cache results of identical prompts for 1 hour. Reduces AI API costs and speeds up repeat requests. | P2 – High | 4 | Not Started | Junior Dev
92 | Performance | Compress API responses (gzip/brotli) | Enable compression middleware in Express. Reduces response payload size by ~70%. | P3 – Medium | 1 | Not Started | Junior Dev
93 | Performance | Preload critical fonts | Add <link rel='preload'> for Dancing Script and any other fonts. Prevents layout shift on load. | P3 – Medium | 1 | Not Started | Junior Dev
94 | Performance | Image optimisation pipeline | All uploaded images auto-compressed to WebP via Cloudflare or Sharp. Max 200KB per image. | P3 – Medium | 3 | Not Started | Junior Dev
95 | SEO & Social Meta | Add meta tags to all public pages | Title, description, og:image, og:title, og:description, twitter:card. Use react-helmet or Vite SSR. | P1 – Critical | 3 | Not Started | Junior Dev
96 | SEO & Social Meta | Create sitemap.xml and robots.txt | Sitemap submitted to Google Search Console. robots.txt allows all public pages. | P2 – High | 2 | Not Started | Junior Dev
97 | SEO & Social Meta | Add structured data (JSON-LD) | SoftwareApplication schema on homepage. Helps Google understand what the app does. | P2 – High | 2 | Not Started | Junior Dev
98 | SEO & Social Meta | Submit to Google Search Console | Verify domain ownership. Submit sitemap. Monitor impressions and clicks from day 1. | P3 – Medium | 1 | Not Started | Junior Dev
99 | SEO & Social Meta | Create landing page / marketing page | Public landing page (not behind auth): hero, features, pricing, testimonials. Currently all content is behind login. | P3 – Medium | 8 | Not Started | Junior Dev
100 | Legal & Compliance | Write Terms & Conditions page | Must be live before accepting payments. Cover: usage, AI-generated content ownership, refund policy. | P1 – Critical | 3 | Not Started | Junior Dev
101 | Legal & Compliance | Write Privacy Policy page | DPDP Act 2023 (India) compliance. State: what data collected, how stored, deletion rights. | P1 – Critical | 3 | Not Started | Junior Dev
102 | Legal & Compliance | Add cookie consent banner | Required for EU users (GDPR). Use CookieYes free tier. Non-essential cookies only after consent. | P1 – Critical | 1 | Not Started | Junior Dev
103 | Legal & Compliance | Register company / GST | Need GSTIN for Razorpay live account and invoices. Consult CA if not already registered. | P2 – High | 0 | Not Started | Junior Dev
104 | Legal & Compliance | AI content disclosure | Add disclaimer: 'Scripts are AI-generated. Review before posting.' Required by emerging AI content laws. | P2 – High | 1 | Not Started | Junior Dev
105 | Legal & Compliance | Data deletion flow | Users can request account + data deletion (DPDP requirement). Build 'Delete Account' in settings. | P3 – Medium | 3 | Not Started | Junior Dev
106 | Accessibility | Add alt text to all images and icons | All <img> tags need descriptive alt. Icon-only buttons need aria-label. Screen reader usable. | P1 – Critical | 2 | Not Started | Junior Dev
107 | Accessibility | Fix colour contrast ratios | Run WCAG contrast checker on all text/background combos. Minimum 4.5:1 for body text. Gradient text is risky. | P2 – High | 3 | Not Started | Junior Dev
108 | Accessibility | Add skip-to-content link | Hidden link that appears on Tab press. Lets keyboard users skip nav to main content. | P2 – High | 1 | Not Started | Junior Dev
109 | Accessibility | ARIA roles on dynamic content | Modal dialogs: role='dialog', aria-modal='true'. Live regions for AI streaming text: aria-live='polite'. | P3 – Medium | 3 | Not Started | Junior Dev
110 | Accessibility | Focus management in modals | When modal opens, focus moves inside. When closed, focus returns to trigger. Prevents keyboard-user confusion. | P3 – Medium | 2 | Not Started | Junior Dev
111 | PWA & Offline | Add PWA manifest.json | name, short_name, icons (192px + 512px), theme_color, background_color, display:'standalone'. Enables 'Add to Home Screen'. | P1 – Critical | 2 | Not Started | Junior Dev
112 | PWA & Offline | Register service worker | Cache app shell (HTML, CSS, JS) for instant offline load. Use Workbox via Vite PWA plugin. | P2 – High | 4 | Not Started | Junior Dev
113 | PWA & Offline | Add offline fallback page | When offline: show cached scripts and a friendly 'You're offline' message instead of browser error. | P2 – High | 3 | Not Started | Junior Dev
114 | PWA & Offline | Enable push notifications | Ask permission after user generates first script. Send: 'Your weekly content tip is ready!' Drives re-engagement. | P3 – Medium | 5 | Not Started | Junior Dev
115 | PWA & Offline | Test install flow on Android + iOS | Verify 'Add to Home Screen' prompt triggers on Android Chrome. iOS requires manual share > Add to Home. | P4 – Low | 2 | Not Started | Junior Dev